## BecomeFoundation
evolve@become.foundation | Become Foundation's mission is to make security awareness training easy and effective for enterprises. By bringing together learning expertise, data science and automation, we allow enterprises to embrace success.

## How to use
How to use this Risk Assessment Template:
1. Fill the relevant information on the Introduction sheet.
2. Add items to the Risk Assessment sheet, and give each item a Risk Level and a Impact Level value between 1 and 100.
3. Use the Results Matrix to see which items Should be addressed first.
4. List proposed controls and a due date for each item on the Results Matrix sheet.
5. Adjust the template to suit your specific needs.

## Introduction
Organization | MetaCubez | List of Participants
Jimmy Essel (IT Lead)
Executive Summary | During the period from August 10, 2024, to August 12, 2024, a comprehensive information security risk assessment was conducted on MetaCubez’s IT Infrastructure, specifically focusing on cloud storage and network systems. MetaCubez relies heavily on cloud-based storage solutions and a complex network infrastructure to manage its operations, including customer data management, internal communications, and financial transactions.
Abdulrahman Fatao (Security Specialist)
The assessment identified several medium to high-risk items that require management’s immediate attention to enhance the security posture of the organization. These risks pertain primarily to data protection, access control mechanisms, and network security. Implementing the recommended controls will significantly mitigate the identified risks and ensure the continuity and security of MetaCubez’s critical IT systems.
Prupose of Assessment | To identify potential vulnerabilities, assess the likelihood and impact of various threats, and recommend mitigation strategies to enhance the security of MetaCubez’s IT environment.
Bob Johnson (Compliance Officer)
Security Program | MetaCubez has a basic security program in place, including firewalls, antivirus software, and regular password changes.
Questionnaire | A survey was sent to all employees to gather information on data handling practices.
Additional Tools | Vulnerability scanning software, such as Nmap and Lynis, were used to identify potential weaknesses.
Risk Model | Qualitative analysis using a risk matrix.
IT Enviornment | Windows-based network with cloud-based storage and applications.
Technology | Microsoft Office 365, AWS cloud storage
Users | Employees, contractors, customers.
Data | Personal data, financial records, customer information.

## Risk Assessment
Asset | Owner | Vulnerabilities | Threats | Potential Impact | Risk Level | Impact Level | Assessment Date | Notes
Database | IT Lead | Access Control | Phishing, Shared Passwords. | Data Leak | 5 | 10 | 2024-11-08 | Regular backups, access controls in place.
Cloud Storage | Security team | Data Encryption | Unauthorized Access, data Breach | Data Leak, Reputation Damage | 4 | 5 | 2024-11-08 | Encryption enabled, access controls in place.
Network | Network Admin | Firewall Configuration | Hacking, Malware | Network Downtime | 6 | 6 | 2024-11-08 | Firewall rules reviewed, password policy enforced.
Web Application | Dev Team | Input Validation | SQL Injection, XSS Attack | Data Leak, Reputation Damage | 7 | 8 | 2024-12-08 | Input validation implemented, authentication strengthened.
Email System | IT Support | Spam Filtering | Phishing, Malware | Financial Loss, Data Leak | 7 | 6 | 13/08/2024 | Spam filtering enabled, authentication strengthened

## Results Matrix
Asset | Priotiy | Existing Control | Proposed Controls | Owner | Due Date | Notes
Database | 50 | Password Changes | IAM Management Solution | IT Lead | 2024-10-12 | Implement IAM solution to enhance access controls.
Cloud Storage | 71 | Encryption, Access controls | Data loss prevention tool, Regular security audits | Security team | 2024-10-08 | Implement data loss prevention tool to detect unauthorized data transfers.
Network | 56 | Firewall rules, Password policy | Network segmentation, Regular security audits | Network Admin | 2024-11-08 | Implement network segmentation to reduce attack surface
Web Application | 64 | Input validation, Authentication | Web application firewall, Regular security audits | Dev Team | 2024-12-08 | Implement web application firewall to detect common web attacks.
Email System | 58 | Password policy, Authentication | Regular security audits, encryption | IT Support | 2024-12-08 | Implement full-disk encryption to protect data at rest.